## Cover
Rollout and Adoption Workbook
for the Office 365 IT Pro or Project Manager
This workbook provides step-by-step guidance for successfully rolling out Office 365 to your organization. Included are detailed steps for each phase, along with recommendations, best practices, and samples for optimal results.
Customize this workbook by adding tasks and timelines to meet your organizational requirements.
Use the Status tab to track rollout progress and to share results with key stakeholders.
©2013 Microsoft Corporation. All rights reserved. The materials are provided for your informational purposes. Microsoft makes no warranties, express or implied. You may copy, modify, distribute and display all materials contained in this “Rollout and Adoption Workbook” solely for your internal and non-commercial use, and only in support of Microsoft technologies. Such use is conditioned upon your compliance with Requirements for Allowed Uses under the Use of Microsoft Copyrighted Content policy.

## Status
Phase | Purpose | % Complete
Project Scope | Define Office 365 goals, deployment and rollout strategy | 25% | Changing the % Complete automatically updates the status chart below.
Proof of Concept | Evaluate Office 365 as a viable solution to meet organizations needs (lab/testing scenario only) | 20%
Pilot | Validate Office 365, resources, and rollout plans with users in preparation for broad rollout (client loaded on actual desktop | 15%
Enterprise Rollout | Launch Office 365 across all departments and user groups | 10%
Run State | Follow operations plan for all key phases/focus areas, increase user-adoption | 0%

## Project Scope Phase
Readiness Focus Area | Task | Task Owner | Status | Target Completion Date | Resources | Notes
Technical Deployment | Set up your organization for Office 365. |  |  | 12-16 weeks before Enterprise Launch | http://office.microsoft.com/redir/FX103993883.aspx
Planning | Assemble the project team, stakeholders, and executive sponsorship. |  |  | 12-16 weeks before Enterprise Launch
Planning | Identify target deployment groups and rollout milestones. |  |  | 12-16 weeks before Enterprise Launch
Planning | Determine reporting structure, cadence and key stakeholders to report to, throughout your rollout effort. |  |  | 12-16 weeks before Enterprise Launch
Planning | Outline your top 3-5 measurable goals (use SMART goals) and define how you will measure |  |  | 12-16 weeks before Enterprise Launch
Planning | Identify any blockers or concerns which may imact your rollout project. Determine a mitigation strategy for each. |  |  | 12-16 weeks before Enterprise Launch
Planning | Document the general opinion of your end-users regarding new technology acceptance and identify how that will play a role in your pilot, and rollout activities |  |  | 12-16 weeks before Enterprise Launch
Planning | Define the scope of your rollout (workloads, business locations, workgroups, etc) |  |  | 12-16 weeks before Enterprise Launch
Planning | Develop your top-line messaging for your value proposition |  |  | 12-16 weeks before Enterprise Launch
Planning | Develop a plan for budget and devices |  |  | 12-16 weeks before Enterprise Launch
Planning | Create a project plan and timeline based on the recommended phases and associated tasks outlined in this workbook. |  |  | 12-16 weeks before Enterprise Launch
Planning | Present detailed plan, timeline, budget, and mitigation strategies to key stakeholders for approval |  |  | 12-16 weeks before Enterprise Launch
Help Desk | Scope the role of the help desk manager(s) and reps across all phases, defining accountabilities, resources and budget. |  |  | 12-16 weeks before Enterprise Launch
Help Desk | Present and gain approval from help desk management as needed |  |  | 12-16 weeks before Enterprise Launch
Awareness | Scope the role of the marketing department across all phases, defining accountabilities, resources and budget. |  |  | 12-16 weeks before Enterprise Launch
Awareness | Present and gain approval from marketing management as needed |  |  | 12-16 weeks before Enterprise Launch
Training | Scope the role of the training department across all phases, defining accountabilities, resources and budget. |  |  | 12-16 weeks before Enterprise Launch
Training | Present and gain approval from training management as needed |  |  | 12-16 weeks before Enterprise Launch
Operations | Scope your operations plan once your initial rollout is complete |  |  | 12-16 weeks before Enterprise Launch

## Proof of Concept Phase
Readiness Focus Area | Task | Task Owner | Status | Target Completion Date | Resources | Notes
Planning | Identify and document your Proof of Concept success criteria |  |  | 10-12 weeks before Enterprise Launch
Planning | Identify the teams that should be involved in configuring and validating the Proof of Concept deployment |  |  | 10-12 weeks before Enterprise Launch
Planning | Coordinate with infrastructure teams to secure required resourcing |  |  | 10-12 weeks before Enterprise Launch
Planning | Update the Deployment Readiness Report weekly to identify changes in Readiness prior to the Proof of Concept |  |  | 10-12 weeks before Enterprise Launch
Training | Attend Office 365 training for design and administration |  |  | 10-12 weeks before Enterprise Launch
Operations | Coordinate with operations teams to maintain Proof of Concept environment |  |  | 10-12 weeks before Enterprise Launch
Operations | Update the Deployment Readiness Report with new milestones to prepare for Pilot |  |  | weekly during POC

## Pilot Phase
Readiness Focus Area | Task | Task Owner | Status | Target Completion Date | Resources | Notes
Planning | Define pilot program goals, and assemble the pilot project team. |  |  | 8-12 weeks before Enterprise Launch
Planning | Define the pilot success measurement plan. |  |  | 8-12 weeks before Enterprise Launch
Planning | Identify the pilot participants based on suitability. |  |  | 8-12 weeks before Enterprise Launch
Planning | Define the testing plan by outlining the functional and feature testing to be completed by pilot group. |  |  | 8-12 weeks before Enterprise Launch |  | Define the amount of time to devote to testing per week, the features to test, the number of users with which to test, and so on.
Planning | Define the training plan for the pilot group. |  |  | 8-12 weeks before Enterprise Launch |  | Use the same training you will provide for the broader group of users to ensure that training resources are sufficient.
Planning | Define the pilot awareness plan and communication plan for the pilot group. |  |  | 8-12 weeks before Enterprise Launch |  | Use the guidelines and resources on the Awareness tab to help create awareness materials for the pilot.
Planning | Define the support process for the pilot. |  |  | 8-12 weeks before Enterprise Launch |  | Use the pilot as an opportunity to test your support process for the broader rollout.
Planning | Define the pilot feedback plan; outline the feedback loop. |  |  | 8-12 weeks before Enterprise Launch
Planning | Create a pilot project plan and timeline based on the recommended tasks on the Pilot Rollout tab of this workbook. |  |  | 8-12 weeks before Enterprise Launch
Planning | Meet with the training and support teams to communicate your pilot plans. |  |  | 8-12 weeks before Enterprise Launch
Help Desk | Create help desk and/or support team training resources. |  |  | 6-8 weeks before Enterprise Launch |  | Typically includes the same resources that are used to train end users, plus common processes for coding service requests, common issues, and escalations for new products and product versions.
Help Desk | Complete help desk and/or support team training sessions. |  |  | 6-8 weeks before Enterprise Launch
Help Desk | Identify and prepare updates for the internal help desk and/or support team site. |  |  | 6-8 weeks before Enterprise Launch |  | New products and product versions require updated content on the help desk and/or support team site. Also, you might need a new forum entry so that help desk and/or support has a common place for discussing issues and resolutions.
Awareness | Publicize sign-up for potential pilot participants. |  |  | 6-8 weeks before Enterprise Launch
Awareness | Send email to those accepted and not accepted pilot invitation. |  |  | 6-8 weeks before Enterprise Launch
Awareness | Publish updates to the internal help desk and/or support team site. |  |  | 6-8 weeks before Enterprise Launch
Awareness | Send email to pilot participants announcing the upcoming migration to Office 365. |  |  | 6-8 weeks before Enterprise Launch
Awareness | Send a welcome email with links to training, Office 365 champions, and support resources. |  |  | 6-8 weeks before Enterprise Launch
Awareness | Send weekly Scenario Spotlight emails to expose users to high-productivity scenarios. |  |  | 6-8 weeks before Enterprise Launch
Awareness | Publish the Scenario Spotlight online form weekly, and collect feedback. |  |  | 6-8 weeks before Enterprise Launch
Awareness | Makes changes to email communications, intranet site, and newsletters based on pilot user feedback. |  |  | 6-8 weeks before Enterprise Launch
Awareness | Send regular emails including an online survey about experiences with Office 365 and devices. |  |  | 6-8 weeks before Enterprise Launch
Awareness | Conduct pilot kick-off meeting to set pilot expectations and communicate detail |  |  | 6-8 weeks before Enterprise Launch
Training | Develop or customize pilot participant resources to meet your organization's needs. |  |  | 6-8 weeks before Enterprise Launch
Training | Conduct training for Office 365 champions, help desk representatives, and project team. |  |  | 6 weeks before Enterprise launch
Training | Make updates to training plans and resources based on pilot user feedback. |  |  | 2-6 weeks before Enterprise launch
Training | Provide locally printed copies of end user Help and training resources to pilot participants. |  |  | 6 weeks before Enterprise launch
Operations | Publish the online pilot sign-up form. |  |  | 6 weeks before Enterprise launch
Operations | Roll out Office 365 and devices to pilot participants. |  |  | 6 weeks before Enterprise launch
Operations | Conduct the pilot. |  |  | 2-6 weeks before Enterprise launch
Operations | Make changes to deployment based on pilot user feedback. |  |  | 2-6 weeks before Enterprise launch
Operations | Gather success metrics, and do a post-pilot assessment. |  |  | 1-2 weeks before Enterprise launch
Operations | As necessary, modify checklists and other resources for next phase of deployment. |  |  | 1-2 weeks before Enterprise launch
Operations | Report out on Pilot success metrics and update success criteria report weekly based on findings |  |  | Weekly during pilot
Operations | Update the Deployment Readiness Report with new milestones to prepare for broad launch |  |  | 2-4 weeks before Enterprise launch

## Enterprise Rollout Phase
Readiness Focus Area | Task | Task Owner | Status | Target Completion Date | Resources | Notes
Planning | Confirm your rollout approach (by workload, by user location, by defined groups, etc) and the associated rollout timeline for each group. |  |  | 4-6 weeks before launch
Planning | Determine your broad-reach awareness strategy and training strategy. |  |  | 4-6 weeks before launch
Planning | Determine how to target specific groups, and identify any needs for customized communications/training and the appropriate timing. |  |  | 4-6 weeks before launch |  | Be sure to provide customized communications to groups with the highest change management requirements, for example, users who are moving from other business tools to Office.
Planning | Define the awareness channels you will leverage. |  |  | 4-6 weeks before launch |  | Channels might include awareness emails, your intranet site, your champions program, newsletters, posters, and a broad launch event. Involve an executive sponsor in as many channels as possible. Have email communications come from the sponsor, or have the sponsor welcome attendees at the launch event.
Planning | Create a timeline for executing the rollout plan. |  |  | 4-6 weeks before launch
Help Desk | Prepare and publish updates to the help desk and/or support team site, including FAQs and other resources updated from pilot phase. |  |  | 2 weeks before launch
Awareness | Recruit champions from the existing pilot participants, and establish a champions program. |  |  | 4-6 weeks before launch |  | Leverage champions to: - Monitor an Office 365 specific distribution list - Maintain a FAQ or blog on your internal site - Host regular brown-bag sessions
Awareness | Create an Office 365 specific email distribution list. |  |  | 4-6 weeks before launch
Awareness | Develop and/or customize tools and applications to generate interest (for example, IM an Expert). |  |  | 2-4 weeks before launch
Awareness | Develop a dedicated Office 365 intranet page. |  |  | 2-4 weeks before launch
Awareness | Develop and/or customize resources for the Office 365 intranet page, including the Setup Checklist for End Users, Frequently Asked Questions, and blog. |  |  | 2-4 weeks before launch
Awareness | Develop and/or customize videos for the Office 365 intranet page. |  |  | 2-4 weeks before launch
Awareness | Add the Setup Checklist for End Users to the Office 365 intranet page. |  |  | 2-4 weeks before launch
Awareness | Develop and/or customize awareness print resources; include support, training, and feedback options in all awareness resources. |  |  | 2-4 weeks before launch
Awareness | Create launch announcements for intranet and IT support sites. |  |  | 2-4 weeks before launch
Awareness | Hold brown-bag sessions. |  |  | 2-4 weeks before launch |  | Invite champions to present at brown-bag sessions.
Awareness | Print and distribute awareness resources. |  |  | 2-4 weeks before launch
Awareness | Publish the dedicated Office 365 intranet page and its associated resources (frequently asked questions (FAQ), blog, videos, and so on). |  |  | 1 week before launch
Awareness | Publish launch announcements on intranet and IT support sites. |  |  | 1 week before launch
Awareness | Hold kickoff event for each rollout group. |  |  | Rollout day
Awareness | Monitor the Office 365 intranet page, and update FAQ and blog content. |  |  | Rollout day and ongoing
Awareness | Publish Office 365 tips in newsletter articles and other periodic communications. |  |  | Rollout day and ongoing
Awareness | Send email announcing the upcoming migration to Office 365. |  |  | 1 week before launch
Awareness | Send welcome email with links to support resources and training offerings. |  |  | Launch day
Training | Develop and/or customize the initial set of end user Help and training resources based on your organization's needs. |  |  | 6-8 weeks before launch
Training | Determine the end user getting started tasks, and develop and/or customize the Setup Checklist for End Users. |  |  | 6-8 weeks before launch
Training | Identify updates to the internal help desk and/or support team site based on pilot feedback. |  |  | 2-4 weeks before launch
Training | Update end user Help and training print resources based on pilot feedback. |  |  | 2-4 weeks before launch
Training | Provide training to Office 365 champions and support staff, and assign them to groups of users. |  |  | 2 weeks before launch
Training | Publish online end user training offerings. |  |  | 1 week before launch
Training | Conduct end user training sessions. |  |  | Post-launch
Training | Meet with the training and support teams to communicate training and support plans for the rollout. |  |  | 6-8 weeks before launch
Training | Identify the Office 365 end user training courses you will use. |  |  | 6-8 weeks before launch
Operations | Monitor usage, user feedback, support calls during each rollout phase, measuring success before moving onto next phase. |  |  | Post-launch and ongoing
Operations | Update the Deployment Readiness Report as needed to identify changes in Readiness during each phase of the Enterprise Rollout. |  |  | weekly during launch phase

## Run State Phase
Readiness Focus Area | Task | Task Owner | Status | Target Completion Date | Resources | Notes
Planning | Revisit goals and success metrics defined during the Project Scope phase. Ensure you have a plan to measure, track progress and adjust as needed, based on results. |  |  | Post-rollout; then quarterly
Planning | Define the operations plan (including how you will pilot, launch and support new releases), and determine the resources you will provide to staff who support Office 365 technologies. |  |  | 1-2 weeks before Enterprise launch
Planning | Outline plan to onboard new employees to Office 365. |  |  | 1-2 weeks before Enterprise launch
Help Desk | Ensure help desk is equipped with resources and staff to support end-users. |  |  | 1-2 weeks before Enterprise launch
Help Desk | Create plan to onboard new help desk staff. |  |  | 4-6 weeks before launch
Help Desk | Extensively train the help desk staff hands-on the product features and top anticipated call generators |  |  | 2-4 weeks before launch
Awareness | Request feedback/success stories from users, to share in quarterly newsletters/communications |  |  | Post-rollout; every 4 weeks
Awareness | Send quarterly updates to users re: newsletter or other communicaton channel. |  |  | Post-rollout; every 4 weeks
Training | Monitor and update training resources as needed, to ensure materials are up-to-date. |  |  | Post-rollout; every 2 weeks
Training | Have small classroom style hands-on sessions where employees walk through scenarios to learn and experiment with various product features. |  |  | Post-rollout; every 4 weeks
Operations | Verify that product is up-to-date with latest cumulative updates. |  |  | Post-rollout; every 12 weeks
Operations | Update scripts for the internal help desk team as needed based on support calls. |  |  | Post-rollout and ongoing
Operations | Implement a taxonomy and tracking system for Office 365 support tickets. |  |  | Post-rollout and ongoing
Operations | Update the FAQ on the dedicated Office 365 intranet site based on support calls. |  |  | Post-rollout and ongoing |  | Post to your intranet or within other defined awareness channels.
Operations | Collect usage and adoption data through Monitoring Sever statistics and user surveys (see ROI) |  |  | Post-rollout and weekly ongoing
Operations | Execute on support strategy (including monitoring and reporting out on support calls, assessing areas for improvement based on call volume), awareness and training strategies. |  |  | Post-rollout and ongoing
Operations | Update the Run State Readiness Report to identify changes in Readiness for Run State. |  |  | weekly or as needed

## Awareness Worksheet
Communication Name or Title | Audience | Key Message | Milestone or Frequency | Start Date | Delivery Mechnism | Reviewer | Sender | Replace [sample text] with your awareness plan information
[Pilot sign-up] | [Pilot users] | [Introduce Office 365 features and functionality] | [Pilot Kickoff] | [11/1/2013] | [Presentation] | [A. Darrow] | [N/A]
[First Touch Event Deck] | [End users] | [Introduce Office 365 features and functionality] | [First Touch Event] | [11/14/2013] | [Presentation] | [M. Kaur] | [N/A]
[Scenario Spotlight] | [End users] | [Showcase Office 365 top use cases] | [Weekly] | [11/14/2013] | [Email] | [Rollout team] | [Exec. Sponsor]