## ProjectDetails
Title | RequestID | ApprovedDate | Status | ProjectedStartDate | ProjectedEndDate | ProjectedDays | ActualDays | PMAssigned
Mobile devices for sales team | 1 | 2016-09-22 | Completed | 2016-10-11 | 2016-11-07 | 20 | 35 | Irvin Sayers
Monitor upgrade - finance department | 2 | 2016-02-03 | Completed | 2016-02-11 | 2016-03-04 | 17 | 18 | Joni Sherman
New version of CRM system | 3 | 2016-10-17 | Completed | 2016-10-25 | 2016-12-20 | 41 | 52 | Irvin Sayers
New tablets for designers | 4 | 2016-08-15 | Completed | 2016-09-12 | 2016-10-17 | 26 | 30 | Irvin Sayers
Mobile devices for HR team | 5 | 2016-02-15 | Completed | 2016-03-01 | 2016-05-04 | 47 | 55 | Irvin Sayers
CAD software for engineering | 6 | 2016-11-30 | Completed | 2016-12-05 | 2017-01-10 | 27 | 30 | Joni Sherman
Mobile devices for finance team | 7 | 2016-10-20 | Completed | 2016-10-28 | 2016-12-27 | 43 | 38 | Joni Sherman
Cloud-based ERP | 8 | 2016-11-11 | In progress | 2017-01-09 | 2017-01-23 | 11 |  | Irvin Sayers
New version of productivity software | 9 | 2016-06-15 | Completed | 2016-06-20 | 2016-09-05 | 56 | 42 | Irvin Sayers
Monitor upgrade - sales | 10 | 2016-06-06 | Completed | 2016-06-15 | 2016-07-20 | 26 | 34 | Irvin Sayers
Mobile devices for engineering team | 11 | 2016-09-27 | Not started |  |  |  |  | Unassigned
New BI software | 12 | 2016-12-05 | Not started |  |  |  |  | Unassigned
Desktop upgrade for finance | 14 | 2016-10-04 | Completed | 2016-10-10 | 2016-11-03 | 19 | 18 | Joni Sherman
Desktop upgrade for marketing | 15 | 2016-11-10 | Completed | 2016-11-18 | 2016-12-13 | 18 | 28 | Irvin Sayers
Mobile devices for analytics team | 17 | 2016-01-12 | Completed | 2016-01-18 | 2016-02-19 | 25 | 27 | Joni Sherman
New accounting package | 18 | 2016-11-15 | Completed | 2016-11-22 | 2016-12-28 | 27 | 29 | Joni Sherman
Formulas:
ProjectedDays = NETWORKDAYS(ProjectDetails[[#This Row],[ProjectedStartDate]],ProjectDetails[[#This Row],[ProjectedEndDate]])