## Slide 1: Enterprise Agility: Introducing Agile into the Enterprise
Philip Japikse
phil.japikse@telerik.com
MVP, MCSD.Net, MCDBA, CSM, CSP
Patterns & Practices Evangelist
Telerik

## Slide 2: Who am I?
Patterns & Practices Evangelist, Telerik, Inc.
Microsoft MVP
MCSD, MCDBA, CSM, CSP
Coder/Speaker/Writer
Lead Director, Cincinnati .NET User’s Group
Founder, Agile Conferences, Inc.
Contributing Author –
  www.nplus1.org
  “C# 2010 All In One” (Wiley)

## Slide 3: Agile Manifesto
We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value:
Individuals and interactions over processes and tools Working software over comprehensive documentation Customer collaboration over contract negotiation Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.
http://agilemanifesto.org

## Slide 4: (Some) Agile Flavors
Scrum is a framework for developing complex products and systems based on:
  Self Managed Teams
  Iterative Development Planning
  Transparency
eXtreme Programming improves software development through:
  Communication
  Simplicity
  Feedback
  Respect
  Courage

## Slide 5: Opening a Restaurant?
“Pigs” – Committed to the Project
  Product Owner
  Scrum Master
  The Development Team
“Chickens” – Interested in the Project
  Users
  Managers
  Others
Notes: Chicken and pig open a restaurant…
Chickens need to be heard, but decision making is left up to the pigs

## Slide 6: Roles
Scrum Master
  Ensures and Enforces Scrum
  Not an “HR” position
Product Owner
  Sole person responsible for the Product Backlog
  All project items and priorities funnel through the Product Owner
Development Team
  Cross Functional
  Adopt “We” Mentality – sink/swim as a whole
  Co-located
Notes: Scrum Master
  Enforces Scrum
  Values
  Practices
  Rules
  Remove Impediments
  Coach/Mentor
Product Owner
  Keeps the backlog up to date
  Updates prioritization as necessary

## Slide 7: Iterations/Sprints
Predetermined duration of work
  Time boxed, not Scope boxed
Length must stay consistent throughout the development life cycle
  Personal recommendation is 14 days

## Slide 8: Product Backlog
The Product Requirements
Each Item consists of
  Description
  Priority
  Estimate
Dynamic, can be modified at any time
  By the Product Owner
Also includes triaged bugs

## Slide 9: Sprint Backlog
Defines the work items for the sprint
Controlled by the team
Items from Product Backlog can be added

## Slide 10: Burn Down charts
Display of:
  What’s been accomplished
  What is remaining
Updated daily
Transparent to all (Pigs AND Chickens)

## Slide 11: Classic Scrum Lifecycle
Sprint Planning Meeting (2-8 hours)
Sprint (7-30 days)
Daily Standup (15 minutes every day)
Sprint Review (4 Hours)
Sprint Retrospective (4 Hours)
Each Sprint’s goal is to deliver
potentially releasable code

## Slide 12: Sprint Planning
Separated into two parts
  Select Items to pull from the Product Backlog
    Consider only prioritized and well defined items
  How will it be developed
    High level architecture
    Get clarifications from Product Owner
End result is Sprint Backlog

## Slide 13: Daily Standup
Held every day. No EXCEPTIONS!
Only PIGS can speak
Three Questions
  What did you do yesterday
  What are you going to do today
  What’s holding you back
If meeting is lasting longer than 15 minutes, you’re talking too much!
  Sidebars

## Slide 14: Sprint Review
Attended by Pigs and Chickens
Team Demonstrates the Product
Product Owner reviews:
  What was accomplished
  What (if anything) was deferred
  What remains on the Product Backlog
  Updated Release scope

## Slide 15: Sprint Retrospective
Identify
  Successes
  Areas for Improvement
Inspect Everything
  People
  Relationships
  Processes
  Tools
Tackle the most relevant 1-2 items

## Slide 16: Review
Agile is about
  Setting attainable goals
  Preventing death marches through time boxing
  Transparency
Scrum is framework that promotes interaction, communication, and teamwork
XP is about development techniques, and engineering processes

## Slide 17: Can’t we all just get along?
Courtesy and Respect
Teams don’t work in isolation
Teams must interact with many other groups in the enterprise that
  Typically are not agile and/or
  Have no desire/ability to become agile
  Don’t assume they don’t “get it”!
Be agile in your interactions
Disclaimer: Some of the concepts in the following slides are not traditional Scrum

## Slide 18: Inter-Team Communication
Host meetings with representatives from all affected teams on a regular schedule
  Development team reports:
    High level progress status
    Reaffirms architecture
  Other teams report:
    Status of infrastructure required for release
    Any changes to external requirements
Meet more often as release gets closer

## Slide 19: Product Release Planning
Used mostly in Enterprise Organizations
  Facilitates Team coordination
Based on existing knowledge
Time-box the release
  Priorities and scope will change
  Estimates will be wrong
Involves
  Product Owner, Architect(s), Security, Infrastructure, QA, etc.
Notes: Used to determine length of project, development staff required, additional resources

## Slide 20: Users
Most users/customers don’t understand software development
Used to waiting months/years to see projects delivered
Coaching is required
  Product Owner is their single Point Of Contact
  User Testing of Sprints is a new concept
Notes:     Users are not to interact with the team directly
    A vital part of the rapid feedback loop is User Testing

## Slide 21: User Testing
User Testing is used to validate the state of the software after every sprint.
  Key Users should be testing the codebase from the previous sprint
  The Team (via the Product Owner) must fully disclose what they believe to be working and not working
Users can enter potential defects into the tracking system

## Slide 22: QA/Testers
Best if QA is co-located with the team
Create Test Plans based on each Sprint
  Not on requirements that might never be developed
When developers believe they are “Done”
  QA Reviews Unit Tests/Peer Review
Bottom line, QA should be Proactive, and not Reactive

## Slide 23: Bug Triage
Bug triage meetings happen immediately after the Daily Standup
Triage Team
  Lead QA, Architect/Dev Lead, Product Owner
Bugs are marked for either:
  Sprint Backlog
  Product Backlog
    Bug
    Change Request
Notes: (if feature is part of the sprint, and the Triage Team feels it needs to be resolved)

## Slide 24: Swim Lanes
Instead of Burn Down Charts
“Stolen” from Kanban
Tasks/Features move from
  In Queue
  In Process
  Ready for QA
  Ready for UAT
  Ready for Release

## Slide 25: Refining Requirements
A good requirement is one that you can wrap a test around
All Backlog items need to be defined well enough that a:
  Developer can understand and code the intent
  QA Resource/Tester can validate the code
Incomplete items are removed

## Slide 26: Wireframes
Used to visually layout the User Interface
All proposed screens
Important to not look “finished”
Tools:
  http://www.mockupscreens.com
  http://www.balsamiq.com
  http://tinyurl.com/mssketchflow

## Slide 27: Designers
Typically create comps very early in the process
  Then go away
They are part of the team
  Start with wireframes
  Designs/comps done at the last responsible moment

## Slide 28: User Stories
User Stories
  As an [X] I Want [Y] So That [Z]1
    X is a role
    Y is a feature
    Z is the benefit
1http://dannorth.net/introducing-bdd
As an Account Manager, I want to be able to Edit a Customer’s Address so that we can Effectively Communicate with them
Includes success criteria

## Slide 29: Success Criteria
Must be testable
Use Given/When/Then syntax
  Given 2000 customers
  When selecting one
  Then the form should open in < 1 second

## Slide 30: Context Specification1
When Editing a Customers Address
  It Should Load in < 1 sec with 2000 customer records
  It Should allow an Account Manager to edit the address
  1Behavior Driven Development (Code Magazine) - Scott Bellware

## Slide 31: Defining “Done”
All (Dev, Users, QA, etc) must agree on definition of Done
  Developer
    Unit Tests, Documentation, Code Reviews, etc
  QA
    Integration Testing, Black Box Testing, etc
  Users
    UAT
Will be different based on the product
  NASA vs XBOX

## Slide 32: Test/Behavior Driven Development
Development needs to be Test Driven
  QA personnel need to understand what that means
Successful T/BDD development teams build confidence in themselves and with others
  QA shouldn’t have to test that
    Math.Add(2,3) returns 5
  QA can focus on the bigger picture
    Making sure the requirements are met
    Integration Testing

## Slide 33: Pair Programming
Slightly reduces productivity
Increases code quality
Should be polygamous
Don’t do it full-time
Notes:   Constant Code Reviews
Checks and Balances

## Slide 34: Sprint 0
Also referred to as the Foundational Sprint
Occurs before full Team is formed
  Product Owner, Application Architect
Used for:
  Configuration (e.g. Build Server, developer Virtuals)
  Product Backlog creation
  Acquiring Funding
  Release/Hardware planning
  Assembling the Development Team

## Slide 35: Verification Sprint
Occurs after code “chill”
Used for:
  Security audits
  Performance/Load/UAT/Integration testing
  Deployment documentation
Team uses this time to work on:
  Required documentation, improving Unit Tests, etc.
  NOT refactoring application code

## Slide 36: Summary
Survive the waterfall
Play nice with others
Bring success to the table, it will spread

## Slide 37: Contact Me
phil@telerik.com
www.skimedic.com/blog
www.twitter.com/skimedic
Telerik
www.twitter.com/Telerik
www.facebook.com/Telerik

## Slide 38: Stay up to date with MSDN Belux
Register for our newsletters and stay up to date: http://www.msdn-newsletters.be
  Technical updates
  Event announcements and registration
  Top downloads
Follow our blog http://blogs.msdn.com/belux
Join us on Facebook http://www.facebook.com/msdnbe http://www.facebook.com/msdnbelux
LinkedIn: http://linkd.in/msdnbelux/
Twitter: @msdnbelux
Download MSDN/TechNet Desktop Gadget http://bit.ly/msdntngadget
Notes: Please keep this slide

## Slide 39: TechDays 2011 On-Demand
Watch this session on-demand via Channel9 http://channel9.msdn.com/belux
Download to your favorite MP3 or video player
Get access to slides and recommended resources by the speakers

## Slide 40: THANK YOU
Stop by the Telerik Booth and say “hi”